## Cover
Click Here to Start
Project Administration

## Home
BACKGROUND
Large business projects can be complex and hard to hold together, even by experienced managers and executives. This workbook contains tools designed to communicate and coordinate information critical to keeping the team aligned and the activities on schedule. Included are:
An administration plan to help the team stay in contact
A task sheet to identify who is accountable for each project task
A master calendar, to align schedule expectations
A Gantt chart to indicate sequencing and task relationships
A resource cost estimator
A charter to ensure everyone is aligned around what is being done and why
NOTE: All pages are protected without a password, to avoid unintentional entries but to allow editing
Project Administration
Cover
Start
Home
Note on Accuracy and Precision
A series of tools related to operational effectiveness and efficiency, financial management, and sales are available from ROI-Team.
No warranty is expressed or implied about the suitability of these tools to your situation, and we recommend professional legal and accounting advice if your situation is complex or uncertain.
Copyright © 2007 - 2018 by ROI-Team, Inc. All rights reserved.

## Admin
Administrative Information |  |  |  |  | [Project Identification Number]
Project Name]
Address |  |  | Phone | Fax | E-Mail
Start Date (Monday) | Weeks
2018-06-06 | 6
Consulting Team Members |  | Phone | Mobile | Fax | E-Mail
[AAA]
[BBB]
[CCC]
Internal Team Members |  | Position | Phone | Mobile | E-Mail
[XXX]
[YYY]
[ZZZ]
Executives |  | Position | Phone | Mobile | E-Mail
[Top Client Name]
[Other Decision Maker]
[Other Decision Maker]
Hotel |  |  | Phone | Rate | Comments
Directions
INSTRUCTIONS
Start on this page
Remove example information
Complete all sections that apply:
  Project ID Number
  Project Name
  Address / location
  Start date (often a Monday)
  Consulting team members
  Internal team members
  Executives/clients/decision-makers
  Hotel & Directions
Information entered will be copied to other pages, to be used as needed
Complete 'Tasks' paged
Complete 'Calendar' page
Complete 'GANTT' page Complete 'Resources' page
Print and distribute to team members, as needed
Project Admin Sheet
Prior
Next
Home

## Tasks
Engagement Task Accountability
Project Name]
Consulting Team Members | Key Tasks | Focus Interviews | Diagnostic Plan | Task A | Value Stream Map | Process Flow Maps | Task B | Supply Chain Review | Project Principles | Project Design | Business Case | Team Prep | Logistics Prep | Project Launch | Task 1 | Task 2 | Task 3 | Task 4 | Task 5 | Task 6
[AAA]
[BBB]
[CCC]
Primary
Support
INSTRUCTIONS
Project and team member names are from 'Admin' page
'Key Task' column names and fill shading are for example only - remove these before entering your p[roject information
Enter project tasks in the vertical columns
Assign accountability for each task to specific team members
Shade primary accountability cells black
Shade support role cells gray
Use this chart as a communication tool
Project Task Assignments
Prior
Next
Home

## Calendar
Engagement Calendar
Project Name]
Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
2018-06-06 | 2018-06-07 | 2018-06-08 | 2018-06-09 | 2018-06-10 | 2018-06-11
Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
2018-06-13 | 2018-06-14 | 2018-06-15 | 2018-06-16 | 2018-06-17 | 2018-06-18
Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
2018-06-20 | 2018-06-21 | 2018-06-22 | 2018-06-23 | 2018-06-24 | 2018-06-25
Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
2018-06-27 | 2018-06-28 | 2018-06-29 | 2018-06-30 | 2018-07-01 | 2018-07-02
Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
2018-07-04 | 2018-07-05 | 2018-07-06 | 2018-07-07 | 2018-07-08 | 2018-07-09
Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
2018-07-11 | 2018-07-12 | 2018-07-13 | 2018-07-14 | 2018-07-15 | 2018-07-16
Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
2018-07-18 | 2018-07-19 | 2018-07-20 | 2018-07-21 | 2018-07-22 | 2018-07-23
Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
2018-07-25 | 2018-07-26 | 2018-07-27 | 2018-07-28 | 2018-07-29 | 2018-07-30
Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
2018-08-01 | 2018-08-02 | 2018-08-03 | 2018-08-04 | 2018-08-05 | 2018-08-06
Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
2018-08-08 | 2018-08-09 | 2018-08-10 | 2018-08-11 | 2018-08-12 | 2018-08-13
Formulas:
Tuesday = [Monday]+1
Wednesday = [Tuesday]+1
Thursday = [Wednesday]+1
Friday = [Thursday]+1
Saturday = [Friday]+1
INSTRUCTIONS
Project name and dates are from the 'Admin' page
Enter diagnostic activities, holidays, scheduled events as needed
Post prominently and revise as necessary to ensure coordination, especially for events that involve the whole team, such as executive updates
Project Calendar
Prior
Next
Home

## Gantt
Schedule of Tasks
Project Name]
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11
Task | 2018-06-06 | 2018-06-13 | 2018-06-20 | 2018-06-27 | 2018-07-04 | 2018-07-11 | 2018-07-18 | 2018-07-25 | 2018-08-01 | 2018-08-08 | 2018-08-15
Focus Interviews
Diagnostic Plan
Task A
Value Stream Map
Process Flow Maps
Task B
Supply Chain Review
Project Principles
Project Design
Business Case
Team Prep
Logistics Prep
Project Launch
Task 1
Task 2
Task 3
Task 4
Task 5
Task 6
Teleconferences
Executive presentations
Communications
Formulas:
Week 2 = [Week 1]+7
Week 3 = [Week 2]+7
Week 4 = [Week 3]+7
Week 5 = [Week 4]+7
Week 6 = [Week 5]+7
Week 7 = [Week 6]+7
Week 8 = [Week 7]+7
Week 9 = [Week 8]+7
Week 10 = [Week 9]+7
Week 11 = [Week 10]+7
INSTRUCTIONS
The project name is from the 'Admin' page
Tasks are copied directly from the 'Tasks' page
Fill shading is example - remove it from all date cells before filling in your project
Color days for each task, as needed
Color days for communications and presentations, as needed
Project Gantt Chart
Prior
Next
Home

## Resource
Total Estimated Cost | 78000 | Resources Assigned & Rough Cost Estimate
Total Out of Pocket Cost | 0 | Project Name]
|  |  | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  | Week 7 |  |  | Week 8 | Week 9 | Week 10 | Week 11
|  | Consulting Team Members | 2018-06-06 |  |  |  |  | 2018-06-13 |  |  |  |  | 2018-06-20 |  |  |  |  | 2018-06-27 |  |  |  |  | 2018-07-04 |  |  |  |  | 2018-07-11 |  |  |  | 2018-07-18 |  |  | 2018-07-25 | 2018-08-01 | 2018-08-08 | 2018-08-15
[AAA]
|  | [BBB] | 1 | 1 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | [CCC] | [7 empty] | 1 | 1 |  |  |  | 1 | 1 | 1 | [7 empty] | 1 | 1
|  | Cost per Week | 10000
|  |  | "Full Accounting" |  |  |  |  | "Out of Pocket"
|  | Days of Effort | 26 |  |  |  |  | 0
|  | Man Weeks | 5.2 |  |  |  |  | 0
|  | Per Week | 52000 |  |  |  |  | 0
FALSE
TRUE
TRUE
FALSE
FALSE
|  | Internal Team Members | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  | Week 7 |  |  | Week 8 | Week 9 | Week 10 | Week 11
|  | [XXX] | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 1 | 1
|  | [YYY] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  | [ZZZ] | [7 empty] | 1 | 1 |  |  |  | 1 | 1 | 1 | [7 empty] | 1 | 1
|  | Charge | 2500
|  |  | "Full Accounting" |  |  |  |  | "Out of Pocket"
|  | Days of Effort | 52 |  |  |  |  | 0
|  | Man Weeks | 10.4 |  |  |  |  | 0
|  | Per Week | 26000 |  |  |  |  | 0
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
Formulas:
Week 2 = [Week 1]+7
Week 3 = [Week 2]+7
Week 4 = [Week 3]+7
Week 5 = [Week 4]+7
Week 6 = [Week 5]+7
Week 7 = [Week 6]+7
Week 8 = [Week 7]+7
Week 9 = [Week 8]+7
Week 10 = [Week 9]+7
Week 11 = [Week 10]+7
INSTRUCTIONS
The project name is copied from the 'Admin' page
Consulting and Internal team member names are also copied from the 'Admin' page
This page is used to estimate the level of effort needed
Erase the estimated days (1 and 0.5) from the day cells
Write "1" or "0.5" into any date to indicate a day or half day of work
Write the cost per man week into cells F15 (consultants) and F42 (client internal team members)
Use the check box to indicate an individual represents an out-of-pocket cost
Project Resource Cost Estimator
Prior
Next
Home

## Charter
Project Charter
Title | Process Review & Improvement
Objectives | o Analyze all of our key processes to identify problem areas and develop corrective action plans
o Develop in-house process analysis and management skills
Problem Statement | o Our costs are at least 10% higher than competitors' costs
o Our organization is frustrated by lack of coordination and frequent manufacturing errors
o We do not understand our processes
Possible Root Causes | o Poor handoffs across department lines
o Lack of clarity about who is in charge of what
Action Plan Outline | o Identify all key processes of the organization
o Prioritize these for analysis based on their significance to the business and degree of problems
o Establish a schedule for analysis
o Execute the schedule and with each analysis identify barriers to success and develop a methodology and schedule for improvement
Significant Risks and Dependencies
o Workforce is fully employed, wuth little spare time
o We lack the internal skills to accomplish this type of work
Project Team | TBD
TBD
TBD
TBD
Financial Expectations
Revenue Improvements
Cost Improvements
Asset Improvements
Investment
Analysis Team Comments
Sign Offs
Every project of substance needs a charter, to fix accountabilities and set measurable expectations. This example includes the sort of information needed. More complex projects could use this same high level charter, with supporting detail and individual charters for each separate sub work stream, as the situation warrants. This template is available for modification as needed (you will want to erase all of the sample information and insert your own.)
It is formatted to print (without this text box) and protected without a password in case you need to modify it.
Project Charter
Prior
End
Home